## Priorities
Priority | Area | Current Status | Key Blocker | Next Milestone | Target Date | Notes
1 | Lesson Materials (Nine's 1:1) | Pipeline has flaws — no lesson fully finished | Need to perfect production pipeline | Complete M01-L001 end-to-end as gold standard |  | Dual-purpose: self-paced course + live teaching
2 | Course Lesson Production | M01 L001-L010 have partial artifacts, M02-M08 scaffolded only | Pipeline quality not consistent enough | Lock pipeline with repeatable quality on 3 lessons |  | 180 lessons total across 18 modules
3 | TikTok Video Series | 2 episodes filmed (Classifiers), 8 scripted — scripts need work | Script/prompt quality inconsistent | Improve scripting skill, re-script eps 3-8 |  | Need better research + prompt for consistent output
4 | Website (Next.js) | Local dev — auth, dashboard, marketing routes exist | Not urgent until course ships | Get quiz page and lesson viewer functional |  | No deployment needed yet
5 | Placement Quiz | placement-v0.json exists | Needs integration with website | Connect quiz to Next.js frontend |  | Helps Nine understand student level
6 | Self-Paced Quiz System | Not started | Depends on lesson content being stable | Design quiz schema per lesson |  | Part of each lesson in the course
7 | Thai Image Carousels | Pipeline exists (/produce-carousel) | Content dependent on lesson vocab | Produce carousels for M01 vocab |  | Instagram/TikTok vocabulary posts

## Lesson Pipeline
Lesson ID | Module | Lesson Title | Pipeline Stage | Status | Script Quality | Deck Built | QA Pass | Blocker / Notes | Last Updated
M01-L001 | M01 | Hello and Basic Courtesy | Stage 6 (Assessment QA) | In Progress | Needs review | Yes | Partial | Has artifacts but pipeline not finalised
M01-L002 | M01 | Names and Countries | Stage 6 (Assessment QA) | In Progress | Needs review | Yes | Partial | Same state as L001
M01-L003 | M01 | Pronouns and Who Questions | Stage 6 (Assessment QA) | In Progress | Needs review | Yes | Partial
M01-L004 | M01 | Numbers 0 to 10 | Stage 3 (Deck Build) | In Progress | Needs review | Yes | No
M01-L005 | M01 | What is This? | Stage 1 (Script) | Not Started | — | No | No
M01-L006 | M01 | Basic Directions | Stage 1 (Script) | Not Started | — | No | No
M01-L007 | M01 | Simple Requests | Stage 1 (Script) | Not Started | — | No | No
M01-L008 | M01 | At the Market | Stage 1 (Script) | Not Started | — | No | No
M01-L009 | M01 | Review and Roleplay | Stage 1 (Script) | Not Started | — | No | No
M01-L010 | M01 | Module 1 Assessment | Stage 1 (Script) | Not Started | — | No | No
M02-L001 | M02 |  | Not Started | Not Started
M02-L002 | M02 |  | Not Started | Not Started
M02-L003 | M02 |  | Not Started | Not Started
M02-L004 | M02 |  | Not Started | Not Started
M02-L005 | M02 |  | Not Started | Not Started
M02-L006 | M02 |  | Not Started | Not Started
M02-L007 | M02 |  | Not Started | Not Started
M02-L008 | M02 |  | Not Started | Not Started
M02-L009 | M02 |  | Not Started | Not Started
M02-L010 | M02 |  | Not Started | Not Started
M03-L001 | M03 |  | Not Started | Not Started
M03-L002 | M03 |  | Not Started | Not Started
M03-L003 | M03 |  | Not Started | Not Started
M03-L004 | M03 |  | Not Started | Not Started
M03-L005 | M03 |  | Not Started | Not Started
M03-L006 | M03 |  | Not Started | Not Started
M03-L007 | M03 |  | Not Started | Not Started
M03-L008 | M03 |  | Not Started | Not Started
M03-L009 | M03 |  | Not Started | Not Started
M03-L010 | M03 |  | Not Started | Not Started
M04-L001 | M04 |  | Not Started | Not Started
M04-L002 | M04 |  | Not Started | Not Started
M04-L003 | M04 |  | Not Started | Not Started
M04-L004 | M04 |  | Not Started | Not Started
M04-L005 | M04 |  | Not Started | Not Started
M04-L006 | M04 |  | Not Started | Not Started
M04-L007 | M04 |  | Not Started | Not Started
M04-L008 | M04 |  | Not Started | Not Started
M04-L009 | M04 |  | Not Started | Not Started
M04-L010 | M04 |  | Not Started | Not Started
M05-L001 | M05 |  | Not Started | Not Started
M05-L002 | M05 |  | Not Started | Not Started
M05-L003 | M05 |  | Not Started | Not Started
M05-L004 | M05 |  | Not Started | Not Started
M05-L005 | M05 |  | Not Started | Not Started
M05-L006 | M05 |  | Not Started | Not Started
M05-L007 | M05 |  | Not Started | Not Started
M05-L008 | M05 |  | Not Started | Not Started
M05-L009 | M05 |  | Not Started | Not Started
M05-L010 | M05 |  | Not Started | Not Started
M06-L001 | M06 |  | Not Started | Not Started
M06-L002 | M06 |  | Not Started | Not Started
M06-L003 | M06 |  | Not Started | Not Started
M06-L004 | M06 |  | Not Started | Not Started
M06-L005 | M06 |  | Not Started | Not Started
M06-L006 | M06 |  | Not Started | Not Started
M06-L007 | M06 |  | Not Started | Not Started
M06-L008 | M06 |  | Not Started | Not Started
M06-L009 | M06 |  | Not Started | Not Started
M06-L010 | M06 |  | Not Started | Not Started
M07-L001 | M07 |  | Not Started | Not Started
M07-L002 | M07 |  | Not Started | Not Started
M07-L003 | M07 |  | Not Started | Not Started
M07-L004 | M07 |  | Not Started | Not Started
M07-L005 | M07 |  | Not Started | Not Started
M07-L006 | M07 |  | Not Started | Not Started
M07-L007 | M07 |  | Not Started | Not Started
M07-L008 | M07 |  | Not Started | Not Started
M07-L009 | M07 |  | Not Started | Not Started
M07-L010 | M07 |  | Not Started | Not Started
M08-L001 | M08 |  | Not Started | Not Started
M08-L002 | M08 |  | Not Started | Not Started
M08-L003 | M08 |  | Not Started | Not Started
M08-L004 | M08 |  | Not Started | Not Started
M08-L005 | M08 |  | Not Started | Not Started
M08-L006 | M08 |  | Not Started | Not Started
M08-L007 | M08 |  | Not Started | Not Started
M08-L008 | M08 |  | Not Started | Not Started
M08-L009 | M08 |  | Not Started | Not Started
M08-L010 | M08 |  | Not Started | Not Started

## Socials
# | Title | Content Type | Category | Platform(s) | Status | Date Posted | Views | Likes | Link / Notes
PUBLISHED CONTENT — @thaiwith.nine
1 | Why 2 persons but pig bodies? (Classifiers) | Reel / Short | Thai Classifiers | IG, TT | Published |  |  |  | EP01 — Classifiers series
2 | School Subjects in Thai | Carousel | Vocabulary | IG | Published
3 | Why Thai say 'water 2 bottles'? (Classifiers) | Reel / Short | Thai Classifiers | IG, TT | Published |  |  |  | EP02 — Classifiers series
4 | Thai Life Habits | Carousel | Culture | IG | Published
5 | พูด (phûut) / บอก (bàawk) / คุย (khûi) | Reel / Short | Word Comparison | IG, TT | Published |  |  |  | Speaking verbs compared
6 | Thai Prepositions of Place | Carousel | Grammar | IG | Published
7 | คิดว่า (khít-wâa) | Reel / Short | Single Word Deep Dive | IG, TT | Published
8 | รู้ว่า (rúu-wâa) | Reel / Short | Single Word Deep Dive | IG, TT | Published
9 | บอกว่า (bàawk-wâa) | Reel / Short | Single Word Deep Dive | IG, TT | Published
10 | อยู่ (yùu) | Reel / Short | Single Word Deep Dive | IG, TT | Published
11 | หน่อย (nòi) | Reel / Short | Single Word Deep Dive | IG, TT | Published
12 | Family Members in Thai | Carousel | Vocabulary | IG | Published
13 | เกิดอะไรขึ้น (gèert à-rai khûen) | Reel / Short | Phrase Breakdown | IG, TT | Published |  |  |  | What's going on? / What happened?
14 | Giving Directions in Thai | Carousel | Vocabulary | IG | Published
15 | เป็น (bpen) | Reel / Short | Single Word Deep Dive | IG, TT | Published |  |  |  | is / am / are / to be
16 | เลย (loei) — Many Meanings | Reel / Short | Single Word Deep Dive | IG, TT | Published
17 | Thai Slang (Rizz, Slay, Sus, Fire, Dead) | Reel / Short | Slang / Culture | IG, TT | Published
18 | เดียว (diao) — Just / Only / One | Reel / Short | Single Word Deep Dive | IG, TT | Published
19 | เดี๋ยว (dǐieow) — Wait | Reel / Short | Single Word Deep Dive | IG, TT | Published
20 | คือ (kue) | Reel / Short | Single Word Deep Dive | IG, TT | Published |  |  |  | Stop using เป็น for everything
21 | ให้ (hâi) | Reel / Short | Single Word Deep Dive | IG, TT | Published
22 | Diseases and Illnesses in Thai (Part 2) | Carousel | Vocabulary | IG | Published
23 | Thai words with ใจ (jai) — Reel | Reel / Short | Word Family | IG, TT | Published
24 | Diseases and Illnesses in Thai (Part 1) | Carousel | Vocabulary | IG | Published
25 | Thai words with ใจ (jai) — Part 1 | Reel / Short | Word Family | IG, TT | Published
26 | Body Parts in Thai | Carousel | Vocabulary | IG | Published
27 | แต่ (dtàe) — Not just 'but' | Reel / Short | Single Word Deep Dive | IG, TT | Published |  |  |  | But / Since / Only / Up to you
28 | Parts of the Head in Thai | Carousel | Vocabulary | IG | Published
29 | มา & ไป (maa & bpai) | Reel / Short | Word Comparison | IG, TT | Published |  |  |  | Come and go
30 | What's Your Job? Professions Pt 2 | Carousel | Vocabulary | IG | Published
31 | ถ้า (thâa) | Reel / Short | Single Word Deep Dive | IG, TT | Published |  |  |  | Conditions / Warning / What if
32 | What's Your Job? Professions Pt 1 | Carousel | Vocabulary | IG | Published
33 | Weather in Thai | Carousel | Vocabulary | IG | Published
34 | มั้ง (máng) — Maybe / I guess so | Reel / Short | Single Word Deep Dive | IG, TT | Published
35 | Emotions and Feelings in Thai | Carousel | Vocabulary | IG | Published
36 | ยัง (yang) — Still / Not yet / Yet | Reel / Short | Single Word Deep Dive | IG, TT | Published
37 | Household Chores in Thai | Carousel | Vocabulary | IG | Published
38 | กับ vs และ (gàp vs láe) | Reel / Short | Word Comparison | IG, TT | Published
39 | Your Thai Wardrobe | Carousel | Vocabulary | IG | Published |  |  |  | Clothing vocab
40 | แล้ว (láew) — Thai's tiny magic word | Reel / Short | Single Word Deep Dive | IG, TT | Published
41 | 12 Months in Thai | Carousel | Vocabulary | IG | Published
42 | ไม่เป็นไร (mâi bpen rai) — 5 ways Thai say it's ok | Reel / Short | Phrase Breakdown | IG, TT | Published
43 | Animal Names and Their Sounds in Thai | Carousel | Vocabulary | IG | Published
44 | Thai Words for Online Shopping | Carousel | Vocabulary | IG | Published
45 | Thailand's Must Try Tropical Fruits | Carousel | Culture | IG | Published
46 | Public Transport Adventures | Carousel | Culture | IG | Published
47 | Cute Sounding Thai Words | Carousel | Vocabulary | IG | Published
48 | When Thai Words Get Emotional (words with ใจ) | Carousel | Word Family | IG | Published
49 | 7 Days 7 Colors — Thai Daily Colors | Carousel | Culture | IG | Published
50 | 10 Thai Dishes Foreigners Must Try | Carousel | Culture | IG | Published
51 | 10 Thai Words & Phrases Tourists Should Know | Carousel | Vocabulary | IG | Published |  |  |  | First post
PLANNED — Thai Classifiers (Scripts Need Rework)
52 | อัน (an) — Classifier EP03 | Reel / Short | Thai Classifiers | IG, TT, YT | Script Rework
53 | ใบ (bai) vs เล่ม (lem) — EP04 | Reel / Short | Thai Classifiers | IG, TT, YT | Script Rework
54 | คัน (khan) vs เครื่อง (khrûeang) — EP05 | Reel / Short | Thai Classifiers | IG, TT, YT | Script Rework
55 | ลูก (lûuk) vs ชิ้น (chín) — EP06 | Reel / Short | Thai Classifiers | IG, TT, YT | Script Rework
56 | แก้ว (gâaeo) vs ขวด (khùat) — EP07 | Reel / Short | Thai Classifiers | IG, TT, YT | Script Rework
57 | ครั้ง (khráng), รอบ (râwp), ที่ (thîi) — EP08 | Reel / Short | Thai Classifiers | IG, TT, YT | Script Rework
CONTENT IDEAS — Inspired by Competitor Research
| Teaching my partner/friend Thai (series) | Reel / Short | Teaching Series | IG, TT, YT | Idea |  |  |  | Kat Talks Thai does this — very high engagement
| Pop Quiz: Can you read this? (flashcard reveal) | Reel / Short | Quiz / Interactive | IG, TT, YT | Idea |  |  |  | Kat + New both do this format
| One Day One Sentence series | Reel / Short | Daily Sentence | IG, TT, YT | Idea |  |  |  | Thai By New's signature format — 1.5K posts, very consistent
| Thai food ordering vocab (at restaurant) | Reel / Short | Situational Thai | IG, TT, YT | Idea |  |  |  | High search volume, travel niche
| Thai tones explained with minimal pairs | Reel / Short | Pronunciation | IG, TT, YT | Idea |  |  |  | maa/mâa/máa etc — always performs well
| Common mistakes foreigners make in Thai | Reel / Short | Mistakes / Humor | IG, TT, YT | Idea |  |  |  | Relatable hook, high shareability
| Thai script breakdown (consonant classes) | Reel / Short | Thai Script | IG, TT, YT | Idea |  |  |  | Kat does handwritten flashcard reveals
| Thai market survival vocab | Carousel | Situational Thai | IG | Idea |  |  |  | Numbers, bargaining, food names
| What Thai people ACTUALLY say vs textbook | Reel / Short | Real vs Textbook | IG, TT, YT | Idea |  |  |  | Always gets comments + shares
| Polite Thai for tourists (5 phrases) | Reel / Short | Tourist Thai | IG, TT, YT | Idea |  |  |  | Evergreen, high save rate
| Thai tongue twisters | Reel / Short | Fun / Challenge | IG, TT, YT | Idea |  |  |  | Entertaining, shareable
| Day in Bangkok — narrated in Thai with subs | Reel / Short | Immersion / Vlog | IG, TT, YT | Idea |  |  |  | Culture + language combined

## Competitor Accounts
Account | Platform | Followers | Posts | Content Style | What Works Well | Ideas to Adapt
@kat_talks_thai | IG + TT | 108K IG / 320K TT | 522 | Teaching family/son Thai, flashcard reveals, pop quizzes, Thailand travel vlogs, script breakdowns | Teaching-family series gets high engagement; pop quizzes drive comments; travel + language combo | Partner/friend teaching series; pop quiz format; combine travel content with Nine
@thai_lessons_by_new | IG + TT | 21.7K IG | 1,523 | One word at a time to camera, 'One Day One Sentence', grammar breakdowns, classifiers, quizzes | Extreme consistency (1.5K posts); simple repeatable format; Patreon monetisation | High-frequency posting cadence; sentence-of-the-day series; simple thumbnail formula
@thaibychom | IG + YT | ~15K |  | Live Zoom lessons, teacher-led videos, quizzes, idioms, listening practice | Free monthly Zoom classes build community; quiz stories drive engagement | Live teaching clips repurposed as reels; quiz story format
@bananathaiSchool (Kru Smuk) | IG + YT | ~10K |  | Clear grammar explanations, common mistakes, polite particles, script lessons | Extra steps explaining WHY — builds trust; mistake-correction format | Common mistakes series; 'Why Thai people say X' format (Nine already does this)
@learnthaiinstyle | IG | ~8K |  | Word of the day, slang, real-life sentences, cultural facts | Practical everyday focus; cultural context added to vocab | Cultural context carousels (Nine already does Thai Life Habits etc)

## Website & Quiz
Task | Area | Status | Priority | Depends On | Notes
Placement quiz frontend integration | Placement Quiz | Not Started | Med | placement-v0.json schema finalised | Quiz JSON exists, needs UI
Quiz results display + insights for Nine | Placement Quiz | Not Started | Med | Placement quiz frontend | Nine sees student weaknesses
Lesson viewer component | Course Viewer | Not Started | Low | Lesson content stable | Display lesson scripts/decks
Lesson progress tracking | Course Viewer | Not Started | Low | Lesson viewer | Track which lessons completed
Self-paced quiz per lesson | Self-Quiz | Not Started | Low | Quiz schema designed | Not started at all yet
Quiz schema design (per-lesson) | Self-Quiz | Not Started | Med | Lesson content pipeline stable | Needs to match lesson quiz banks
Auth system (login/signup) | Auth | Scaffolded | Low | — | Routes exist, needs implementation
Dashboard layout | Dashboard | Scaffolded | Low | Auth | Route exists
Marketing / landing page | Marketing | Scaffolded | Low | — | Route exists
Pricing page | Marketing | Not Started | Low | Business model decided
Deployment setup | DevOps | Not Started | Low | Course near release | Not needed yet

## Recurring Tasks
Task | Area | Frequency | Automated? | Last Run | Next Due | Owner | Notes
TikTok script + film new episode | TikTok | Weekly? | No |  |  | Oliver + Nine | Cadence TBD
Review & improve pipeline prompts | Course | Weekly? | No |  |  | Oliver | Iterate on agent prompts
Produce next lesson through pipeline | Course | Weekly? | No |  |  | Oliver | Once pipeline is stable
Transliteration audit | Course | Per batch | Yes (CLI) |  |  | Oliver | npm run course:translit-audit
Validate lesson artifacts | Course | Per batch | Yes (CLI) |  |  | Oliver | npm run course:validate
Instagram/TikTok carousel post | Marketing | Weekly? | No |  |  | Nine | /produce-carousel
Review TikTok analytics | TikTok | Weekly? | No |  |  | Oliver | Track what's working
Update this tracker spreadsheet | Admin | Weekly | No |  |  | Oliver | Keep priorities current

## Image Carousels
Topic | Lesson Link | Status | Images Created | Posted To | Date Posted | Notes